## Team
Initials | First | Last | Email | GitHub Username
TM | Trevor | Miranda | tmiranda@stevens.edu | lazorgator
VG | Vaishnavi | Gopalakrishnan | vgopalak@stevens.edu | vaishnavimecit
AS | Amr | Saleh | amrsaleh129@gmail.com | amrnator
|  |  | GitHub Repository: | https://github.com/lazorgator/ssw555-gedcom

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Parse GEDCOM files into objects | TM | Done
1 | US02 | Output information as tables | TM | Done
2 | US03 | Death before birth | TM
2 | US04 | Marriage after death | TM
3 | US05 | Marriage before birth | TM
3 | US06 | Divorce after death | TM
4 | US07 | Divorce before birth | TM
4 | US08 | Less than 130 years old | TM
1 | US09 | Birth before marriage of parents | VG
1 | US10 | Birth before death of parents | VG
2 | US11 | Marriage after 14 | VG
2 | US12 | No bigamy | VG
3 | US13 | Correct gender for role | VG
3 | US14 | List deceased | VG
4 | US15 | List living married | VG
4 | US16 | Reject illegitimate dates | VG
1 | US17 | List all families | AS
1 | US18 | Note gay marriage | AS
2 | US19 | No Polygamy | AS
2 | US20 | No incest | AS
3 | US21 | No Cousin marraige | AS
3 | US22 | Note Levirate marriage | AS
4 | US23 | Note infidelity | AS
4 | US24 | Note long engagements | AS

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2019-02-20 | 22 | 0 | 552 | 6 | 5520

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Parse GEDCOM files into objects | TM | Done | 276 | 3 | 276 | 3 | Yes
US02 | Output information as tables | TM | Done | 276 | 3 | 276 | 3 | Yes
US09 | Birth before marriage of parents | VG
US10 | Birth before death of parents | VG
US17 | List all families | AS
US18 | Note gay marriage | AS
Review Results:
Need a group chat program
Keep doing:
Avoid:

## Sprint 2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US03 | Death before birth | TM
US04 | Marriage after death | TM
US11 | Marriage after 14 | VG
US12 | No bigamy | VG
US19 | No Polygamy | AS
US20 | No incest | AS
Review Results:
Keep doing:
Avoid:

## Sprint 3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US05 | Marriage before birth | TM
US06 | Divorce after death | TM
US13 | Correct gender for role | VG
US14 | List deceased | VG
US21 | No Cousin marraige | AS
US22 | Note Levirate marriage | AS
Review Results:
Keep doing:
Avoid:

## Sprint 4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | Divorce before birth | TM
US08 | Less than 130 years old | TM
US15 | List living married | VG
US16 | Reject illegitimate dates | VG
US23 | note infidelity | AS
US24 | Note long engagements | AS
Review Results:
Keep doing:
Avoid:

## Stories
Story ID | Story Name | Story Description
US01 | Parse GEDCOM files into objects | Parse the GEDCOM file into objects so that we can programmatically access the information in a structured way.
US02 | Output information as tables | Output the GEDCOM information as tables.
US03 | Death before birth | Notify if someone's death occurs before their birth.
US04 | Marriage after death | Notify if a marriage occurs after a spouse's death.
US05 | Marriage before birth | Notify if a marriage occurs before a spouse's birth.
US06 | Divorce after death | Notify if a divorce occurs after a spouse's death.
US07 | Divorce before birth | Notify if a divorce occurs before a spouse's birth.
US08 | Less than 130 years old | Notify if a person is older than 130 years when they die, which is oldler than anyone has ever lived.
US09 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US10 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US11 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US12 | No bigamy | Marriage should not occur during marriage to another spouse
US13 | Correct gender for role | Husband in family should be male and wife in family should be female
US14 | List deceased | List all deceased individuals in a GEDCOM file
US15 | List living married | List all living married people in a GEDCOM file
US16 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)
US17 | List all families | As a user I can see a list of all families in a GEDCOM file
US18 | Note gay marriage | matrimony between members of the same gender will be noted, but not discouraged
US19 | No Polygamy | marriage of multiple spouses will be noted
US20 | No incest | Notify if siblings are married
US21 | No Cousin marraige | Notify if cousins are married
US22 | Note Levirate marriage | Notify if a brother of a deceased man marries his widow
US23 | Note infidelity | Notify if a married person has a child with someone other than their spouse after marriage.
US24 | Note long engagements | Notify if an engagement has gone on for 5 years or more. Just get married already!